METAPET SCHOOLS

Pilot Prospectus

Independent proposal for a classroom trial

## Problem Statement

Australian schools need low-friction classroom tools that help students discuss systems, routines, and online safety habits without adding teacher admin or introducing avoidable privacy and safeguarding risk.

## Pilot Scope

| Parameter | Detail |
| --- | --- |
| Year levels | Years 3–6 |
| Schools | 1 |
| Classes | 1 |
| Lead teacher | 1 |
| Duration | Initial single-class pilot with a stop/go review after the first fortnight |
| Delivery model | Teacher-led classroom use only |

## Pilot Boundaries

- No student accounts

- Alias-only classroom roster

- No social features

- No generative chat

- No always-on companion use

## Evidence Set

- Teacher interview

- Anonymous student exit feedback

- Parent/carer feedback

- Pre/post measure

- Incident log

- Dropout and engagement counts

- Implementation fidelity notes

## Operational Materials

- Acceptance Runbook

- Pilot Runbook

- School Partner Checklist

- Family Participation Protocol

- ICT/Privacy Review Checklist

- Parent Readability Checklist

- End-of-Pilot Summary

## Success Criteria

- Teachers can set up and run the sequence without account administration

- Leadership and ICT reviewers can understand the privacy and safety position quickly

- Students can explain simple system rules, state changes, or online safety habits after the sequence

- No significant safeguarding, privacy, or over-engagement incidents occur

## Stop Conditions

The pilot will be paused or stopped if any of the following occur:

- The school profile exposes non-school product surfaces

- Teachers report unacceptable workload or setup burden

- Families or staff cannot distinguish the school deployment from the broader product

- A privacy or safeguarding issue remains unresolved